## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | [7 empty] | 0
2 | Yes | Manually Scheduled | Supervisor Allocation | 18 days | September 20, 2017 8:00 AM | October 13, 2017 5:00 PM |  | 1
3 | Yes | Auto Scheduled | Regular Supervisor Meetings | 175.13 days | October 16, 2017 8:00 AM | June 18, 2018 9:00 AM |  | 1
4 | Yes | Manually Scheduled | Regular Supervisor Meetings 1 | 1 hr | October 16, 2017 8:00 AM | October 16, 2017 9:00 AM |  | 2
5 | Yes | Manually Scheduled | Regular Supervisor Meetings 2 | 1 hr | October 23, 2017 8:00 AM | October 23, 2017 9:00 AM |  | 2
6 | Yes | Manually Scheduled | Regular Supervisor Meetings 3 | 1 hr | October 30, 2017 8:00 AM | October 30, 2017 9:00 AM |  | 2
7 | Yes | Manually Scheduled | Regular Supervisor Meetings 4 | 1 hr | November 6, 2017 8:00 AM | November 6, 2017 9:00 AM |  | 2
8 | Yes | Manually Scheduled | Regular Supervisor Meetings 5 | 1 hr | November 13, 2017 8:00 AM | November 13, 2017 9:00 AM |  | 2
9 | Yes | Manually Scheduled | Regular Supervisor Meetings 6 | 1 hr | November 20, 2017 8:00 AM | November 20, 2017 9:00 AM |  | 2
10 | Yes | Manually Scheduled | Regular Supervisor Meetings 7 | 1 hr | November 27, 2017 8:00 AM | November 27, 2017 9:00 AM |  | 2
11 | Yes | Manually Scheduled | Regular Supervisor Meetings 8 | 1 hr | December 4, 2017 8:00 AM | December 4, 2017 9:00 AM |  | 2
12 | Yes | Manually Scheduled | Regular Supervisor Meetings 9 | 1 hr | December 11, 2017 8:00 AM | December 11, 2017 9:00 AM |  | 2
13 | Yes | Manually Scheduled | Regular Supervisor Meetings 10 | 1 hr | December 18, 2017 8:00 AM | December 18, 2017 9:00 AM |  | 2
14 | Yes | Manually Scheduled | Regular Supervisor Meetings 11 | 1 hr | December 25, 2017 8:00 AM | December 25, 2017 9:00 AM |  | 2
15 | Yes | Manually Scheduled | Regular Supervisor Meetings 12 | 1 hr | January 1, 2018 8:00 AM | January 1, 2018 9:00 AM |  | 2
16 | Yes | Manually Scheduled | Regular Supervisor Meetings 13 | 1 hr | January 8, 2018 8:00 AM | January 8, 2018 9:00 AM |  | 2
17 | Yes | Manually Scheduled | Regular Supervisor Meetings 14 | 1 hr | January 15, 2018 8:00 AM | January 15, 2018 9:00 AM |  | 2
18 | Yes | Manually Scheduled | Regular Supervisor Meetings 15 | 1 hr | January 22, 2018 8:00 AM | January 22, 2018 9:00 AM |  | 2
19 | Yes | Manually Scheduled | Regular Supervisor Meetings 16 | 1 hr | January 29, 2018 8:00 AM | January 29, 2018 9:00 AM |  | 2
20 | Yes | Manually Scheduled | Regular Supervisor Meetings 17 | 1 hr | February 5, 2018 8:00 AM | February 5, 2018 9:00 AM |  | 2
21 | Yes | Manually Scheduled | Regular Supervisor Meetings 18 | 1 hr | February 12, 2018 8:00 AM | February 12, 2018 9:00 AM |  | 2
22 | Yes | Manually Scheduled | Regular Supervisor Meetings 19 | 1 hr | February 19, 2018 8:00 AM | February 19, 2018 9:00 AM |  | 2
23 | Yes | Manually Scheduled | Regular Supervisor Meetings 20 | 1 hr | February 26, 2018 8:00 AM | February 26, 2018 9:00 AM |  | 2
24 | Yes | Manually Scheduled | Regular Supervisor Meetings 21 | 1 hr | March 5, 2018 8:00 AM | March 5, 2018 9:00 AM |  | 2
25 | Yes | Manually Scheduled | Regular Supervisor Meetings 22 | 1 hr | March 12, 2018 8:00 AM | March 12, 2018 9:00 AM |  | 2
26 | Yes | Manually Scheduled | Regular Supervisor Meetings 23 | 1 hr | March 19, 2018 8:00 AM | March 19, 2018 9:00 AM |  | 2
27 | Yes | Manually Scheduled | Regular Supervisor Meetings 24 | 1 hr | March 26, 2018 8:00 AM | March 26, 2018 9:00 AM |  | 2
28 | Yes | Manually Scheduled | Regular Supervisor Meetings 25 | 1 hr | April 2, 2018 8:00 AM | April 2, 2018 9:00 AM |  | 2
29 | Yes | Manually Scheduled | Regular Supervisor Meetings 26 | 1 hr | April 9, 2018 8:00 AM | April 9, 2018 9:00 AM |  | 2
30 | Yes | Manually Scheduled | Regular Supervisor Meetings 27 | 1 hr | April 16, 2018 8:00 AM | April 16, 2018 9:00 AM |  | 2
31 | Yes | Manually Scheduled | Regular Supervisor Meetings 28 | 1 hr | April 23, 2018 8:00 AM | April 23, 2018 9:00 AM |  | 2
32 | Yes | Manually Scheduled | Regular Supervisor Meetings 29 | 1 hr | April 30, 2018 8:00 AM | April 30, 2018 9:00 AM |  | 2
33 | Yes | Manually Scheduled | Regular Supervisor Meetings 30 | 1 hr | May 7, 2018 8:00 AM | May 7, 2018 9:00 AM |  | 2
34 | Yes | Manually Scheduled | Regular Supervisor Meetings 31 | 1 hr | May 14, 2018 8:00 AM | May 14, 2018 9:00 AM |  | 2
35 | Yes | Manually Scheduled | Regular Supervisor Meetings 32 | 1 hr | May 21, 2018 8:00 AM | May 21, 2018 9:00 AM |  | 2
36 | Yes | Manually Scheduled | Regular Supervisor Meetings 33 | 1 hr | May 28, 2018 8:00 AM | May 28, 2018 9:00 AM |  | 2
37 | Yes | Manually Scheduled | Regular Supervisor Meetings 34 | 1 hr | June 4, 2018 8:00 AM | June 4, 2018 9:00 AM |  | 2
38 | Yes | Manually Scheduled | Regular Supervisor Meetings 35 | 1 hr | June 11, 2018 8:00 AM | June 11, 2018 9:00 AM |  | 2
39 | Yes | Manually Scheduled | Regular Supervisor Meetings 36 | 1 hr | June 18, 2018 8:00 AM | June 18, 2018 9:00 AM |  | 2
40 | Yes | Manually Scheduled | Identify Topic | 23 days | September 13, 2017 8:00 AM | October 13, 2017 5:00 PM |  | 1
41 | Yes | Manually Scheduled | Draft Research Objectives & Research Questions | 7 days | October 17, 2017 8:00 AM | October 25, 2017 5:00 PM | 40 | 1
42 | Yes | Manually Scheduled | Finalize Research Objectives and Questions | 1 day | October 26, 2017 8:00 AM | October 26, 2017 5:00 PM | 41 | 1
43 | Yes | Manually Scheduled | Choose Dissertation Title | 3 days | October 27, 2017 8:00 AM | October 31, 2017 5:00 PM | 42 | 1
44 | Yes | Manually Scheduled | Outline initial scope | 1 day? | October 27, 2017 8:00 AM | October 27, 2017 5:00 PM | 42 | 1
45 | Yes | Manually Scheduled | Preliminary Literature Search & Review | 35 days | October 16, 2017 8:00 AM | December 1, 2017 5:00 PM |  | 1
46 | Yes | Manually Scheduled | Literature Search & Review : Social Media | 35 days | October 16, 2017 8:00 AM | December 1, 2017 5:00 PM |  | 2
47 | Yes | Manually Scheduled | Literature Search & Review : Twitter | 35 days | October 16, 2017 8:00 AM | December 1, 2017 5:00 PM |  | 2
48 | Yes | Manually Scheduled | Literature Search & Review : Sentiment Analysis | 35 days | October 16, 2017 8:00 AM | December 1, 2017 5:00 PM |  | 2
49 | Yes | Manually Scheduled | Literature Search & Review : Technology Release | 35 days | October 16, 2017 8:00 AM | December 1, 2017 5:00 PM |  | 2
50 | Yes | Manually Scheduled | Literature Search & Review : Advertising Campaign | 35 days | October 16, 2017 8:00 AM | December 1, 2017 5:00 PM |  | 2
51 | Yes | Manually Scheduled | Complete Preliminary Literature Search & Review | 0 days | December 4, 2017 8:00 AM | December 4, 2017 8:00 AM | 45 | 1
52 | Yes | Manually Scheduled | Identify Working Hypothesis / Theory | 35 days | October 16, 2017 8:00 AM | December 1, 2017 5:00 PM | 45SS | 1
53 | Yes | Manually Scheduled | Finalize Hypothesis/ Theory | 1 day | December 4, 2017 8:00 AM | December 4, 2017 5:00 PM | 52 | 1
54 | Yes | Manually Scheduled | Define Preliminary Methodology | 1 day | December 4, 2017 8:00 AM | December 4, 2017 5:00 PM | 45SS | 1
55 | Yes | Manually Scheduled | Finalize Preliminary Methodology | 1 day | December 5, 2017 8:00 AM | December 5, 2017 5:00 PM | 54 | 1
56 | Yes | Manually Scheduled | Compile Data Collection Instrument | 15 days | January 17, 2018 8:00 AM | February 6, 2018 5:00 PM | 55 | 1
57 | Yes | Manually Scheduled | Collect Data | 7 days | February 7, 2018 8:00 AM | February 15, 2018 5:00 PM | 56 | 1
58 | Yes | Manually Scheduled | Analyze Data | 15 days | February 16, 2018 8:00 AM | March 8, 2018 5:00 PM | 57 | 1
59 | Yes | Manually Scheduled | Write Proposal Draft: Introduction | 1 day | January 17, 2018 8:00 AM | January 17, 2018 5:00 PM | 44,43 | 1
60 | Yes | Manually Scheduled | Write Proposal Draft: Literature Review | 1 day | December 4, 2017 8:00 AM | December 4, 2017 5:00 PM | 45 | 1
61 | Yes | Manually Scheduled | Write Proposal Draft: Working Theory | 1 day | December 5, 2017 8:00 AM | December 5, 2017 5:00 PM | 53 | 1
62 | Yes | Manually Scheduled | Write Proposal Draft: Proposed Methodology | 1 day | December 6, 2017 8:00 AM | December 6, 2017 5:00 PM | 55 | 1
63 | Yes | Manually Scheduled | Submit and present Dissertation Proposal | 1 day | December 7, 2017 8:00 AM | December 7, 2017 5:00 PM | 62 | 1
64 | Yes | Manually Scheduled | Complete Write up for Initial Chapters: Introduction | 2 days | March 9, 2018 8:00 AM | March 12, 2018 5:00 PM | 58 | 1
65 | Yes | Manually Scheduled | Complete Write up for Initial Chapters: Literature Review | 7 days | March 13, 2018 8:00 AM | March 21, 2018 5:00 PM | 58,60,64 | 1
66 | Yes | Manually Scheduled | Complete Write up for Initial Chapters: Working Theory | 7 days | March 22, 2018 8:00 AM | March 30, 2018 5:00 PM | 58,61,65 | 1
67 | Yes | Manually Scheduled | Complete Write up for Initial Chapters: Proposed Methodology | 7 days | April 2, 2018 8:00 AM | April 10, 2018 5:00 PM | 58,66,62 | 1
68 | Yes | Manually Scheduled | Write Chapters: Data Analysis, Findings & Conclusion | 21 days | April 11, 2018 8:00 AM | May 9, 2018 5:00 PM | 58,67 | 1
69 | Yes | Manually Scheduled | Submit and Present Interim Report and Poster | 45 days | May 10, 2018 8:00 AM | July 11, 2018 5:00 PM | 68 | 1
70 | Yes | Manually Scheduled | Complete Dissertation Write up | 45 days | May 10, 2018 8:00 AM | July 11, 2018 5:00 PM | 68 | 1
71 | Yes | Manually Scheduled | Submit Complete Dissertation | 0 days | July 12, 2018 8:00 AM | July 12, 2018 8:00 AM | 70 | 1

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
1 | Supervisor: Peter Carew` | S | Work |  |  |  |  | 100% | $0.00/h | 0
2 | Padraig Kirwan | P | Work |  |  |  |  | 10% | $0.00/h | 0
3 | Larry Stapleton | L | Work |  |  |  |  | 100% | $0.00/h | 0
4 | Ali Akbar Jilani | A | Work |  |  |  |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Supervisor Allocation | Padraig Kirwan | 0 | 14.4h | 10%
Supervisor Allocation | Ali Akbar Jilani | 0 | 144h | 100%
Regular Supervisor Meetings 1 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 1 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 2 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 2 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 3 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 3 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 4 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 4 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 5 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 5 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 6 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 6 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 7 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 7 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 8 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 8 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 9 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 9 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 10 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 10 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 11 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 11 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 12 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 12 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 13 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 13 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 14 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 14 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 15 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 15 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 16 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 16 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 17 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 17 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 18 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 18 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 19 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 19 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 20 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 20 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 21 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 21 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 22 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 22 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 23 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 23 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 24 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 24 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 25 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 25 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 26 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 26 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 27 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 27 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 28 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 28 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 29 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 29 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 30 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 30 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 31 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 31 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 32 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 32 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 33 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 33 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 34 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 34 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 35 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 35 | Ali Akbar Jilani | 0 | 1h | 100%
Regular Supervisor Meetings 36 | Supervisor: Peter Carew` | 0 | 1h | 100%
Regular Supervisor Meetings 36 | Ali Akbar Jilani | 0 | 1h | 100%
Identify Topic | Ali Akbar Jilani | 0 | 184h | 100%
Draft Research Objectives & Research Questions | Ali Akbar Jilani | 0 | 56h | 100%
Draft Research Objectives & Research Questions | Supervisor: Peter Carew` | 0 | 56h | 100%